## Sheet1
S/N | Task | Date | Li Jianxi (hrs) | Wong Bo Xi Filbert (hrs) | Remarks
1 | Initial Planning and Ideation of the Orbital Project | 2026-03-17 | 2 | 2 | Initial discussion of the project we want to do, as well as the tech stack that is most likely need for this project
2 | Meeting Up on Zoom to discuss the deliverables for the Lift-Off Submissions | 2026-05-16 | 2 | 2 | Did a discussion on what needs to be done for the Lift-Off submissions, where we decided that Filbert will be doing the poster while Jianxi will be doing the video presentation
3 | Poster Creation for Lift-Off Submission | 2026-05-17 | - | 4 | When and utilise tools like Adobe Express where stock images on the Posters were found in the Adobe Express Free Catalogue images for use
2026-05-18
4 | Video and Slide Creation for Lift-Off Submission | 2026-05-17 | 3 | - | Created slides and recorded a video of what we want to achieve in this Orbital Project
2026-05-18
5 | Unity project setup and scene configuration (Mission Control 2 Workshop) | 2026-05-23 | - | 2 | Attended the MissionWissMon Contebinarrol 2 Webinar where I saw how to use Unity, as well as how to build a simple game like Geometry Dash Things learnt include: Learnt Unity concepts needed for the proof of concept, including GameObjects, Components, Rigidbody2D, Colliders, Inspector references, and scene management.
6 | Research on Age of War gameplay mechanics | 2026-05-25 | - | 4 | This includes going to YouTube to see how: - to build designs, in terms of how to get character sprites (From the Unity Asset Store) - how to configure unit movements - how to configure HP bar to name a few - Play the original Game to see how the mechanics work in the actual game
7 | Asset sourcing and initial sprite integration | 2026-05-25 | - | 2 | Sourced suitable placeholder sprites/assets from Unity Asset Store or free asset sources and tested how they could be used in the prototype scene.
8 | Setting up the template of the game layout | 2026-05-26 | - | 4 | Integrated background/base assets, experimented with battlefield length, base placement, spawn-point positions, unit scale, and map layout for the proof-of-concept scene.
9 | Setting up the Units/Base that will be the main component for this game | 2026-05-26 | - | 2 | Created unit/base objects, linked script references in the Inspector, and ensured spawned objects used the correct components and transforms.
10 | Unity layers, tags, and collision mask configuration | 2026-05-27 | - | 2 | Configured tags/layers for Player, Enemy, bases, units, ground, and collision filtering so scripts could distinguish allies, enemies, terrain, and valid attack targets.
11 | Unit deployment and ground physics integration | 2026-05-27 | - | 2 | Implemented basic deployment behaviour where units fall/deploy into the scene and only start moving after they have landed on the ground. (Quite simple since it was thought in the Misson Control 2 Workshop)
12 | Meeting up on Zoom to touch base on what was done and how doable is the project we want to do | 2026-05-28 | 1 | 1 | Filbert showcases his current game state progress
13 | Unit movement implementation | 2026-05-28 | - | 3 | Implemented automatic x-axis movement for units and direction handling based on whether the unit belongs to the player side or enemy side.
14 | Collision detection prototype | 2026-05-28 | - | 2 | Added initial logic for units to detect obstacles/targets and stop when they encounter another object or valid combat target. (Manageable, since the concept it was taught in the Mission Control 2 lecture as well)
15 | Raycast-based enemy and ally detection system | 2026-05-28 | - | 4 | Implemented and refined raycast/collider checks to detect enemies in front, identify same-team units, and decide whether the unit should move, wait, or attack. Took a very long time because understanding how RayCast was used through documentation and tutorials was quite confusing for me at first.
16 | Gameplay camera movement and boundary control | 2026-05-29 | - | 2 | Implemented camera movement, zooming with the scroll wheel, horizontal panning, and boundaries to prevent the camera from moving outside the intended map area. Was more complex than I had expected since I had initially asked the Lecturer for the Mission Control 2 webinar if it was possible to implement this, and he said it was quite easy to do)
17 | Health point bar implementation for units and bases | 2026-05-30 | - | 2 | Implemented HP bars for units and bases. Adapted tutorial-based logic and modified the health bar direction/behaviour for unit and base use cases.
18 | World-space HP bar attachment and synchronization | 2026-05-30 | - | 1 | Adjusted HP bar positioning and update logic so that health bars remain attached to the correct unit/base and update visually when health changes.
19 | Player and enemy unit spawning system | 2026-05-31 | - | 5 | Implemented player spawning using the Z key and enemy time-based spawning. Configured spawn points and spawn-side logic. Realised that my units need to be of prefabs to allow for multiple spawning of the same units without needing to create multiple copies manually
20 | Base destruction and game-state handling | 2026-05-31 | - | 2 | Added checks so units/spawners handle destroyed bases correctly, preventing spawning or attacking logic from continuing after a base is destroyed.
21 | Unit combat interactions and attack loop | 2026-05-31 | - | 5 | Implemented combat interactions between units and bases, including attack range, cooldown timing, target health reduction, and destruction behaviour.
22 | Unit spacing and ally queueing behaviour refinement | 2026-05-31 | - | 4 | Refined behaviour so allied units queue behind one another instead of overlapping or colliding unnecessarily. Added logic to prioritise earlier-spawned units moving forward first.
23 | Refactoring movement and combat scripts for modularity | 2026-05-31 | - | 2 | Cleaned up movement/combat logic and improved script separation so future unit types and additional combat behaviour can be added more easily.
24 | Gameplay testing and balancing | 2026-06-01 | - | 3 | Performed accumulated gameplay testing and fine-tuning for Milestone 1, including spawn behaviour, unit movement, attack timing, base damage, and HP bar display.
25 | Gameplay parameter tuning | 2026-06-01 | - | 1 | Adjusted early prototype parameters such as speed, HP, attack damage, attack range, attack cooldown, spawn rates, and camera boundaries. (Accumulated timing till Milestone 1)
26 | Inline code documentation and maintainability improvements | 2026-06-01 | - | 3 | Added detailed inline comments explaining core implementation reasoning for spawning, raycasting, ally detection, health handling, and combat logic. (Accumulated timing till Milestone 1)
27 | Project log cleanup and submission preparation | 2026-06-01 | - | 1 | Cleaned up the project log, corrected task descriptions, added missing technical work, and prepared deliverables for Milestone 1 submission.
28 | Milestone 1 README expansion and project documentation | 2026-06-01 |  | - | Writing of Milestone 1 README documentation
- | TOTAL HOURS WORKED | 2026-06-01 | 8 | 67 | Summary of Total Hours worked thus Far